## Unfinished Work
ID | Priority | Category | Item | Source File | Effort Est. | Status | Notes
BUG-A1 | CRITICAL | Bug | Archetype required but unmarked — silently blocks "Create Story" | hero_creator_step.dart | 1-2 hrs | Fixed | Fixed by 44a96ad (2026-04-12)
B2 | CRITICAL | Bug | Companion assets load from wrong folder (adventurer/) for older bands | companion_selector_step.dart | 2-3 hrs | Fixed | Fixed — assets in per-band folders, resolver uses band.name
H1 | CRITICAL | Bug | Scenario card images 404 in production | assets/images/scenarios/ | 2-3 hrs | Fixed | Fixed — all scenario images exist and declared in pubspec
H2 | CRITICAL | Bug | TypeError during wizard (cannot read toString of undefined) | wizard flow | 2-4 hrs | Fixed | Code inspection shows all .toString() calls are null-safe. Likely fixed in March bug sprint. Needs prod runtime verification.
H3 | CRITICAL | Infra | No live Gemini health probe — only checks config | health endpoints | 2-3 hrs | Fixed | Fixed — health endpoint does live _client.models.get() probe
H4 | CRITICAL | Testing | Production smoke tests not re-run after CORS fix | CI/CD | 1-2 hrs | Fixed | Prod smoke tests pass 2026-04-14. Age gate fix local-only — needs Railway deploy.
C-1 | CRITICAL | UX | Archetype chips white-on-white (unreadable) — M3 theme bug | hero_creator_step.dart ~L3428 | 1-2 hrs | Fixed | Fixed by 0b593ff + be8c4b6 (M3 WidgetStateProperty)
C-2 | CRITICAL | UX | Review avatar overflow — yellow-black stripe "ERFLOWED P" | magic_review_step.dart:1940 | < 1 hr | Fixed | Fixed by 8865c23 (UX-C2 avatar overflow)
S-2 | HIGH | UX | Step nav tabs non-functional — tap changes indicator but no scroll | hero_creator_step.dart | 2-3 hrs | Fixed | Fixed by ae31049 (UX-C1 — step nav taps scroll accordion)
S-3 | HIGH | UX | Setting selection binding off-by-one on review | magic_review_step.dart | 2-3 hrs | Fixed | Scenario selection is ID-based end-to-end (string IDs, not indices). No off-by-one possible.
M-1 | HIGH | Legal | Name entry appears BEFORE parental consent (COPPA risk) | screen flow | 1-2 hrs | Fixed | Fixed by 0005b01 (2026-04-13) — name persisted after consent
CI-1 | HIGH | Infra | CI/CD pipeline broken — dependency mismatch + test paths wrong | GitHub Actions | 2-3 hrs | Fixed | All test paths exist (backend/tests/api, security, unit, integration; test/unit/services). May have been fixed.
S-1 | MEDIUM | UX | Companions section absent from Creator band | hero_creator_step.dart | 2-3 hrs | Fixed | Fixed by dc4b03a (Companions section added to Creator accordion)
UX-A1 | MEDIUM | UX | Wizard background wrong color for Adolescent (hardcoded purple) | wizard_story_screen.dart | < 1 hr | Fixed | Fixed by 44a96ad (2026-04-12)
UX-A2 | MEDIUM | UX | "ADVENTURE TEAM" label — age-regressive for 16yo | hero_creator_step.dart | < 1 hr | Fixed | Fixed by 44a96ad (2026-04-12)
UX-A3 | MEDIUM | UX | Adolescent band identical to Creator — no differentiation | wizard flow | 3-4 hrs | Fixed | Fixed by 44a96ad (2026-04-12)
UX-A4 | MEDIUM | UX | No genre/tone selection for Adolescent band | hero_creator_step.dart | 1-2 hrs | Fixed | Fixed by 44a96ad (2026-04-12)
UX-A5 | MEDIUM | UX | Character-desire prompt missing on Adolescent (Creator-only guard) | hero_creator_step.dart | < 1 hr | Fixed | Fixed by 44a96ad (2026-04-12)
BUG-A2 | MEDIUM | UX | Review shows "—" for missing archetype/scenario | magic_review_step.dart | 1 hr | Fixed
ISAR | MEDIUM | Code | 7 TODOs: Isar web support disabled — avatar persistence broken on web | avatar_service.dart | Blocked | Fixed | AvatarCacheEntrysStub added to web stub; _effectiveIsar fallback in AvatarService; all 7 TODOs un-commented.
MR-1 | LOW | UX | Summary card accent borders (blue/gold/purple/pink) | magic_review_step.dart | 1-2 hrs | Fixed | Fixed 504266d — _SummaryRow border uses colorAccent; distinct per-row colour
MR-2 | LOW | UX | Summary card shimmer animation | magic_review_step.dart | 1-2 hrs | Fixed | Fixed 504266d — story-type row shimmer (Adventurer + default review)
MR-3 | LOW | UX | Stagger-reveal animation for summary rows | magic_review_step.dart | 1 hr | Fixed | Already done via _StaggeredReveal on all summary rows
MR-4 | LOW | UX | Companion avatar thumbnails inline on review | magic_review_step.dart | 1 hr | Fixed | Fixed 504266d — leadingWidget on _PitchRow; Creator Cast row shows companion thumbnail
ADULT-1 | MEDIUM | Feature | Adult World Bible for top 3 scenarios | story engine | 3-4 hrs | Fixed
ADULT-2 | MEDIUM | Feature | Adult Thematic Question field + UI | hero_creator_step.dart | 2-3 hrs | Fixed
ADULT-3 | LOW | Feature | Adult meditation section (zero emotional support flow) | new screen | 6-8 hrs | Deferred
SUMMARY | Critical |  | High |  | Medium

## Repo Cleanup
Category | Item | Action | Priority | Notes
Zero-byte files | characters.db | Delete | HIGH | Empty, unused
Zero-byte files | devstory-weaver-appbackendapp.db | Delete | HIGH | Malformed filename, 0 bytes
Zero-byte files | devstory-weaver-appinstanceapp.db | Delete | HIGH | Malformed filename, 0 bytes
Zero-byte files | conflict_resolution_data.dart | Delete | HIGH | Empty, unused
Windows artifacts | New folder/ | Delete | HIGH | Empty — just desktop.ini
Windows artifacts | New folder (2)/ | Delete | HIGH | Empty — just desktop.ini
Stale files | commit_msg.txt | Delete | MEDIUM | Old commit message
Stale files | .git-commit-msg.txt | Delete | MEDIUM | Old commit message
Stale files | avatar_luna_20251223_084527.png (1.6MB) | Delete | MEDIUM | Dated test avatar
Stale files | thePlaceholderImageBeforeCharacterGeneration.jpeg | Delete | MEDIUM | Placeholder, 553KB
Root sprawl | 18 generate_*.py scripts | Move to scripts/generation/ | HIGH | Asset generation scripts
Root sprawl | 26 test_*.py / run_*.py scripts | Move to scripts/testing/ | HIGH | Test & verification scripts
Root sprawl | 10 debug/check/extract scripts | Move to scripts/debug/ | MEDIUM | Debug & diagnostic tools
Root sprawl | 17 setup/fix/utility scripts | Move to scripts/util/ | MEDIUM | Setup, fix, audit scripts
Root sprawl | 6 .bat/.sh maintenance scripts | Move to scripts/maintenance/ | MEDIUM | Git/branch cleanup scripts
Misplaced files | full_image_replacement_prompts.md | Move to docs/ | LOW
Misplaced files | gemini_prompts_only.md | Move to docs/ | LOW
Misplaced files | step1-8.png screenshots | Move to docs/screenshots/ | LOW | ~1.7MB total
Misplaced files | fresh_load.png | Move to docs/screenshots/ | LOW
Doc sprawl | 10+ deployment guides → 1 DEPLOYMENT_GUIDE.md | Consolidate | MEDIUM | Keep latest, archive rest
Doc sprawl | 16 test reports → 1 TEST_RESULTS.md | Consolidate | MEDIUM | Keep latest, archive rest
Doc sprawl | 10 session handoffs → archive older ones | Archive | LOW | Keep only current + SESSION_HISTORY
Doc sprawl | 14 avatar docs → 2-3 comprehensive guides | Consolidate | LOW
Doc sprawl | Duplicate API.md + API_ENDPOINTS.md | Merge | LOW
Doc sprawl | Total: 194 docs → target ~50 | Full audit | LOW | Major project
Stale docs | PROJECT_STATUS.md (last updated Nov 2025) | Update | HIGH | 5 months stale
Stale docs | SESSION_HISTORY.md (last entry Mar 6) | Update | MEDIUM | 5 weeks stale

## Testing Gaps
Category | Tests Needed | Effort Est. | Priority | Status
Integration Tests | 42 | 8-12 hrs | HIGH | Not Started
Frontend Screen Tests | 30 | 6-8 hrs | HIGH | Not Started
Performance Tests | 10 | 6-8 hrs | MEDIUM | Not Started
Service Tests | 20 | 4-6 hrs | MEDIUM | Not Started
Cross-Browser Tests | 5 | 3-4 hrs | MEDIUM | Not Started
Accessibility Tests | 10 | 4-5 hrs | MEDIUM | Not Started
Security Hardening | 0 | 6-8 hrs | HIGH | Not Started
Content Quality (15 stories) | 0 | 6-8 hrs | MEDIUM | Not Started
TOTAL TESTS |  | ~50-65 hrs